## DAILY REPORT
Date | 2026-06-04 | [6 empty] | CC6
Contractor Plant Identification No/ Идентификационный No завода Подрядчика |  | Contractor Project No / No Проекта Подрядчика |  |  | Owner Plant Identification No / Идентификационный No завода Заказчика |  |  | Owner Project No./ No Проекта Заказчика
Fluid Catalytic Cracker Unit (FCC)
Project Document No. / No проектного документа |  | Issue / Выпуск |  |  | Owner Document No / No документа Заказчика
No. | 165 | IFI
PROJECT:
DAILY PROGRESS REPORT
[21 empty] | Update: | 2026-06-05
Information about downtime
Information on forced downtime of equipment
№ | Construction Area | [5 empty] | Downtime (pcs.) |  |  |  |  | Number of machines/hours |  |  |  | Reason for downtime
Information on forced downtime of personal*
№ п/п | Personnel Description | [5 empty] | Downtime (man) |  |  |  |  | Number of h/hours |  |  |  | Reason for downtime
Temperature Min |  |  | 21 | ID / Идентификатор работы графика | L1Subcon / Подрядчик | L2Subcon / Субподрядчик | Title Description / Описание титула | Construction Work Area / Зона строительства | Position / Технол. Позиция | Discipline / Дисциплина | Work type / Вид работ | Activity Name / Название работы | UOM / Ед. изм. | Project Scope / Общий объем (ФО) | Daily Quantity Progress / Прогресс за день (ФО) | Cum. Quantity Progress / Накопит. прогресс (ФО) | Manpower | Direct - Indirect / Рабочий - ИТР | On site - off site / на площадке - вне площадки | HSE Report | Daily | Overall
Temperature Max |  |  | 12 | 1 | CC6 | CC6/CC6 | 605 | Overall | Overall | Overall | Overall | Preparation work | - | - | - | - | 117 | Indirect | On site
Weather Condition |  |  | sunny | 2 | CC6 | CC6/CC6 | 605 | Overall | Overall | Overall | Overall | Preparation work | - | - | - | - | 15 | Indirect | Off site
Wind |  |  | <3rd | 3 | CC6 | CC6/Othere Country | 605/608 | Overall | Overall | Overall | Overall | Preparation work | - | - | - | - | 82 | Direct | On site |  |  |  | 30 driver 30 mid asians 22 Bengalis
|  |  |  | 4 | CC6 | CC6/CC6 | 605 | Overall | Overall | Mechanical | Critical and heavy | Preparation work | - | - | - | - | 15 | Direct | On site
General Personnel Summary / Общая сводка по мобилизации персонала |  |  |  | 5 | CC6 | CC6/CC6 | 605 | Overall | Overall | Civil | AG Concrete | Preparation work | - | - | - | - | 77 | Direct | On site
Total Manhours / Всего ч/ч |  |  | 11430 | 6 | CC6 | CC6/CC6 | 605 | Overall | Overall | Civil | AG Concrete | Preparation work | - | - | - | - | 27 | Direct | Off site
Total Direct / Всего рабочий персонал |  |  | 1011 | 7 | CC6 | CC6/CC6 | 605 | Overall | Overall | Steel Structures | Primary Steel Structures | Preparation work | - | - | - | - | 79 | Direct | On site | Type of Machinery
Direct on Site / Рабочий персонал на площадке |  |  | 784 | 8 | CC6 | CC6/CC6 | 605 | Overall | Overall | Steel Structures | Primary Steel Structures | Preparation work | - | - | - | - | 10 | Direct | Off site | Crane | 23
Direct off site / Рабчий персонал вне площадки |  |  | 227 | 9 | CC6 | CC6/CC6 | 605 | Overall | Overall | Overall | Overall | Preparation work | - | - | - | - | 161 | Direct | On site | Loader | 3
Total Inderect / Всего непрямой персонал (ИТР) |  |  | 132 | 10 | CC6 | CC6/CC6 | 605 | Overall | Overall | Overall | Overall | Overall | - | - | - | - | 84 | Direct | Off site | Flatbed truck | 5 |  | rest Immigration Bureau
On site |  |  |  | 11 | CC6 | CC6/CC6 | 605 | 605-018 | KM | Steel Structures | Primary Steel Structures | Preparation work | - | - | - | - | 3 | Direct | On site | Aerial Work Platforms | 3
Indirect Personnel / Непрямой персонал |  |  | 117 | 12 | CC6 | CC6/CC6 | 605 | 605-010 | KMA | Steel Structures | Primary Steel Structures | Installation | tn | 377 | 20 | 40 | 9 | Direct | On site | Excavator | 5
Direct Personnel / Рабочий персонал |  |  | 784 | 13 | CC6 | CC6/CC6 | 605 | 605-024 | KMA | Steel Structures | Primary Steel Structures | Preparation work | - | - | - | - | 6 | Direct | On site | Forklift | 1
Off site |  |  |  | 14 | CC6 | CC6/CC6 | 605/608 | 000-000 | Overall | General | Backfilling | Backfilling | m3 | 99256 | 100 | 43250 | 15 | Direct | On site | Road roller
Indirect Personnel / Непрямой персонал |  |  | 15 | 15 | CC6 | CC6/CC6 | 608 | 608-017 | KM | Steel Structures | Primary Steel Structures | Installation | tn | 169 | 0.53 | 72.03 | 6 | Direct | On site
Direct Personnel / Рабочий персонал |  |  | 227 | 16 | CC6 | CC6/CC6 | 608 | 608-010 | KM | Steel Structures | Primary Steel Structures | Preparation work | - | - | - | - | 4 | Direct | On site
|  |  |  | 17 | CC6 | CC6/CC6 | 608 | 608-000 | Overall | UG Works | UG Piping Carbon Steel | Preparation work | - | - | - | - | 9 | Direct | On site
|  |  |  | 18 | CC6 | CC6/CC6 | 605 | 605-001 | 1-R-101 | Mechanical | Critical and heavy | Inspection | - | - | - | - | 4 | Direct | On site
|  |  |  | 19 | CC6 | CC6/CC6 | 605 | 605-006 | KM | Steel Structures | Primary Steel Structures | Installation | tn | 731 | 16.4 | 246.04 | 17 | Direct | On site
|  |  |  | 20 | CC6 | CC6/CC6 | 605 | 605-007 | KM | Steel Structures | Primary Steel Structures | Preparation work | - | - | - | - | 6 | Direct | On site
|  |  |  | 21 | CC6 | CC6/CC6 | 605 | 605-019 | Overall | General | UG Piping Carbon Steel | Preparation work | - | - | - | - | 5 | Direct | On site
|  |  |  | 22 | CC6 | CC6/CC6 | 605 | 605-019 | KM | Steel Structures | Primary Steel Structures | Installation | tn | 657 | 26.1 | 131.79 | 11 | Direct | On site
|  |  |  | 23 | CC6 | CC6/CC6 | 605 | 605-023 | KMA | Steel Structures | Primary Steel Structures | Installation | tn | 275 | 0.83 | 30.17 | 11 | Direct | On site
|  |  |  | 24 | CC6 | CC6/CC6 | 605 | 605-020 | KM | Steel Structures | Primary Steel Structures | Installation | tn | 1112 | 11.46 | 763.93 | 13 | Direct | On site
|  |  |  | 25 | CC6 | CC6/CC6 | 605 | 605-001 | KM | Steel Structures | Primary Steel Structures | Installation | tn | 1790 | 5.4 | 1024.14 | 6 | Direct | On site
|  |  |  | 26 | CC6 | CC6/CC6 | 608 | 608-009 | Overall | Civil | AG Concrete | Preparation work | - | - | - | - | 20 | Direct | On site
|  |  |  | 27 | CC6 | CC6/CC6 | 605 | 605-013 | Overall | Civil | AG Concrete | Preparation work | - | - | - | - | 27 | Direct | On site
|  |  |  | 28 | CC6 | CC6/CC6 | 605 | 605-023 | Overall | Civil | AG Concrete | Preparation work | - | - | - | - | 8 | Direct | On site
|  |  |  | 29 | CC6 | CC6/CC6 | 605 | 605-019 | Overall | Civil | UG Concrete | Preparation work | - | - | - | - | 2 | Direct | On site
|  |  |  | 30 | CC6 | CC6/CC6 | 608 | 608-015 | Overall | Civil | AG Concrete | Preparation work | - | - | - | - | 3 | Direct | On site
|  |  |  | 31 | CC6 | CC6/CC6 | 608 | 608-013 | РCм1 | Civil | UG Concrete | Formwork | % | 100 | 80 | 80 | 20 | Direct | On site
|  |  |  | 32 | CC6 | CC6/CC6 | 608 | 608-013 | РCм2 | Civil | UG Concrete | Formwork | % | 100 | 80 | 80
|  |  |  | 33 | CC6 | CC6/CC6 | 608 | 608-013 | РCм3 | Civil | UG Concrete | Formwork | % | 100 | 80 | 80
|  |  |  | 34 | CC6 | CC6/CC6 | 608 | 608-012 | ФOм1 | Civil | UG Concrete | Preparation work | - | - | - | - | 11 | Direct | On site
|  |  |  | 35 | CC6 | CC6/CC6 | 605 | 605-022 | Overall | Civil | AG Concrete | Preparation work | - | - | - | - | 21 | Direct | On site
|  |  |  | 36 | CC6 | CC6/CC6 | 608 | 608-001 | РCм1 | Civil | UG Concrete | Preparation work | - | - | - | - | 6 | Direct | On site
|  |  |  | 37 | CC6 | CC6/CC6 | 608 | 608-016 | Overall | Civil | UG Concrete | Preparation work | - | - | - | - | 15 | Direct | On site
|  |  |  | 38 | CC6 | CC6/CC6 | 605 | 605-016 | ПPм1 | Civil | UG Concrete | Formwork | % | 100 | 10 | 25 | 16 | Direct | On site
|  |  |  | 39 | CC6 | CC6/CC6 | 605 | 605-007 | ПФM 3 | Civil | UG Concrete | Preparation work | - | - | - | - | 10 | Direct | On site
|  |  |  | 40 | CC6 | CC6/CC6 | 605 | 605-005 | Overall | Civil | AG Concrete | Preparation work | - | - | - | - | 10 | Direct | On site
|  |  |  | 41 | CC6 | CC6/CC6 | 605 | 605-003 | Бм1a | Civil | AG Concrete | Reinforcement | tn | 3.35 | 1.35 | 1.35 | 16 | Direct | On site
|  |  |  | 42 | CC6 | CC6/CC6 | 605 | 605-003 | Бм1г | Civil | AG Concrete | Reinforcement | tn | 3.33 | 1.33 | 1.33
|  |  |  | 43 | CC6 | CC6/CC6 | 605 | 605-011 | Overall | Civil | AG Concrete | Preparation work | - | - | - | - | 15 | Direct | On site
|  |  |  | 44 | CC6 | CC6/CC6 | 605 | 605-009 | Overall | Civil | AG Concrete | Preparation work | - | - | - | - | 45 | Direct | On site
|  |  |  | 45 | CC6 | CC6/CC6 | 608 | 608-011 | РCм1 | Civil | UG Concrete | Concrete pouring | m3 | 158.65 | 132 | 132
|  |  |  | 46 | CC6 | CC6/CC6 | 608 | 608-011 | РCм2 | Civil | UG Concrete | Concrete pouring | m3 | 56.44 | 37.7 | 37.7
|  |  |  | 47 | CC6 | CC6/CC6 | 608 | 608-011 | РCм3 | Civil | UG Concrete | Concrete pouring | m3 | 59.86 | 52.38 | 52.38
|  |  |  | 48 | CC6 | CC6/CC6 | 608 | 608-011 | РCм4 | Civil | UG Concrete | Concrete pouring | m3 | 31.09 | 26.19 | 26.19
|  |  |  | 49 | CC6 | CC6/CC6 | 608 | 608-011 | РCм5 | Civil | UG Concrete | Concrete pouring | m3 | 29.93 | 26.19 | 26.19
|  |  |  | 50 | CC6 | CC6/CC6 | 608 | 608-011 | РCм6 | Civil | UG Concrete | Concrete pouring | m3 | 13.16 | 11.4 | 11.4
|  |  |  | 51 | CC6 | CC6/CC6 | 608 | 608-011 | РCм7 | Civil | UG Concrete | Concrete pouring | m3 | 30.92 | 27.2 | 27.2
|  |  |  | 52 | CC6 | CC6/CC6 | 608 | 608-011 | РCм8 | Civil | UG Concrete | Concrete pouring | m3 | 15.28 | 11.6 | 11.6
|  |  |  | 53 | CC6 | CC6/CC6 | 608 | 608-011 | РCм9 | Civil | UG Concrete | Concrete pouring | m3 | 11.3 | 9.6 | 9.6
|  |  |  | 54 | CC6 | CC6/CC6 | 608 | 608-011 | РCм10 | Civil | UG Concrete | Concrete pouring | m3 | 13.36 | 11.6 | 11.6
|  |  |  | 55 | CC6 | CC6/CC6 | 608 | 608-011 | РCм11 | Civil | UG Concrete | Concrete pouring | m3 | 22.6 | 19.2 | 19.2
|  |  |  | 56 | CC6 | CC6/CC6 | 608 | 608-011 | РCм13 | Civil | UG Concrete | Concrete pouring | m3 | 12.92 | 10.8 | 10.8
|  |  |  | 57 | CC6 | CC6/CC6 | 608 | 608-011 | РCм14 | Civil | UG Concrete | Concrete pouring | m3 | 10.32 | 8.8 | 8.8
|  |  |  | 58 | CC6 | CC6/CC6 | 605 | 605-001 | Overall | Civil | AG Piping - PREFAB | Welding | DI | 24534 | 12 | 3953.2 | 106 | Direct | Off site
|  |  |  | 59 | CC6 | CC6/CC6 | 605 | 605-002 | Overall | Civil | AG Piping - PREFAB | Welding | DI | 11384 | 8 | 2189.6
|  |  |  | 60 | CC6 | CC6/CC6 | 605 | 605-003 | Overall | Civil | AG Piping - PREFAB | Welding | DI | 44788 | 186 | 11575.2
|  |  |  | 61 | CC6 | CC6/CC6 | 605 | 605-005 | Overall | Civil | AG Piping - PREFAB | Welding | DI | 21838 | 16 | 5639.8
|  |  |  | 62 | CC6 | CC6/CC6 | 605 | 605-007 | Overall | Civil | AG Piping - PREFAB | Welding | DI | 1791 | 17.6 | 382.8
|  |  |  | 63 | CC6 | CC6/CC6 | 605 | 605-008 | Overall | Civil | AG Piping - PREFAB | Welding | DI | 22330 | 34.4 | 4823.2
|  |  |  | 64 | CC6 | CC6/CC6 | 605 | 605-009 | Overall | Civil | AG Piping - PREFAB | Welding | DI | 31718 | 86 | 8334.6
|  |  |  | 65 | CC6 | CC6/CC6 | 605 | 605-010 | Overall | Civil | AG Piping - PREFAB | Welding | DI | 21078 | 8 | 6150.6
|  |  |  | 66 | CC6 | CC6/CC6 | 605 | 605-015 | Overall | Civil | AG Piping - PREFAB | Welding | DI | 6739 | 32 | 1872.4
|  |  |  | 67 | CC6 | CC6/CC6 | 605 | 605-018 | Overall | Civil | AG Piping - PREFAB | Welding | DI | 10050 | 20 | 3274.4
|  |  |  | 68 | CC6 | CC6/CC6 | 605 | 605-022 | Overall | Civil | AG Piping - PREFAB | Welding | DI | 32941 | 54.4 | 7814.4
|  |  |  | 69 | CC6 | CC6/CC6 | 605 | 605-023 | Overall | Civil | AG Piping - PREFAB | Welding | DI | 11759 | 10 | 3223.2
|  |  |  | 70 | CC6 | CC6/CC6 | 608 | 608-008 | Overall | Civil | AG Piping - PREFAB | Welding | DI | 10345 | 50 | 2268
|  |  |  | 71 | CC6 | CC6/CC6 | 608 | 608-009 | Overall | Civil | AG Piping - PREFAB | Welding | DI | 12922 | 16 | 1440
|  |  |  | 72 | CC6 | CC6/CC6 | 608 | 608-010 | Overall | Civil | AG Piping - PREFAB | Welding | DI | 23755 | 16 | 1745.2
|  |  |  | 73 | CC6 | CC6/CC6 | 608 | 608-015 | Overall | Civil | AG Piping - PREFAB | Welding | DI | 18645 | 10 | 842
|  |  |  | 74 | CC6 | CC6/CC6 | 761 | 761-511 | Overall | Civil | AG Piping - PREFAB | Welding | DI | 59602 | 54 | 8338
[20 empty] | Total Machinery |  | 40
·
Report Number :
[END OF DOCUMENT / КОНЕЦ ДОКУМЕНТА]
Note on Z39: 吊车 160T履带吊 30T吊车 2 25T吊车 2 400T 55T 30T 3 80T
Note on Y40: 装载机
Note on Y41: 平板车
Note on Y42: 曲臂车
Note on Y43: 挖掘机
Note on Y44: 叉车

## Lists
Discipline / Дисциплина | Work type / Вид работ | Activity Name / Название работы | UOM / Ед. изм. | Direct - Indirect / Рабочий - ИТР | On site - off site / на площадке - вне площадки
Civil | Piling | Preparation work | PCS | Direct | On site
UG Works | UG Concrete | Driven | m2 | Indirect | Off site
Steel Structures | AG Concrete | Headcut | m3
Piping | Pre-cast Concrete | Lean concrete | %
Electrical & Instrumentation | Primary Steel Structures | Reinforcement | tn
General | Secondary Steel Structures | Formwork | m
Mechanical | UG Piping Carbon Steel | Concrete pouring | DI
Painting & Insulation | UG Piping HDPE | Installation | -
Building | Manholes | Bolt tightening
Overall | AG Piping - PREFAB | Grout release
| AG Piping - SITE | Inspection
| Backfilling | Excavation
| Excavation | Pipeline or manholes inst.
| Grounding / Earthing and Lightning | Backfilling
| Critical and heavy | Welding
Static Equipment
Rotating Equipment
Instrumentation Cable pulling
Ductwork
HVAC mian equipment
False floor
Fire Fighting Works - Main Equipment
Passive Fire Protection (touch-up)
Roads & Paving - Concrete
Installations in the field
Insulation
Cladding
Overall