## DAILY REPORT
Date | 2026-06-05 | [6 empty] | CC6
Contractor Plant Identification No/ Идентификационный No завода Подрядчика |  | Contractor Project No / No Проекта Подрядчика |  |  | Owner Plant Identification No / Идентификационный No завода Заказчика |  |  | Owner Project No./ No Проекта Заказчика
Fluid Catalytic Cracker Unit (FCC)
Project Document No. / No проектного документа |  | Issue / Выпуск |  |  | Owner Document No / No документа Заказчика
No. | 166 | IFI
PROJECT:
DAILY PROGRESS REPORT
[21 empty] | Update: | 2026-06-06
Information about downtime
Information on forced downtime of equipment
№ | Construction Area | [5 empty] | Downtime (pcs.) |  |  |  |  | Number of machines/hours |  |  |  | Reason for downtime
Information on forced downtime of personal*
№ п/п | Personnel Description | [5 empty] | Downtime (man) |  |  |  |  | Number of h/hours |  |  |  | Reason for downtime
Temperature Min |  |  | 17 | ID / Идентификатор работы графика | L1Subcon / Подрядчик | L2Subcon / Субподрядчик | Title Description / Описание титула | Construction Work Area / Зона строительства | Position / Технол. Позиция | Discipline / Дисциплина | Work type / Вид работ | Activity Name / Название работы | UOM / Ед. изм. | Project Scope / Общий объем (ФО) | Daily Quantity Progress / Прогресс за день (ФО) | Cum. Quantity Progress / Накопит. прогресс (ФО) | Manpower | Direct - Indirect / Рабочий - ИТР | On site - off site / на площадке - вне площадки | HSE Report | Daily | Overall
Temperature Max |  |  | 11 | 1 | CC6 | CC6/CC6 | 605 | Overall | Overall | Overall | Overall | Preparation work | - | - | - | - | 117 | Indirect | On site
Weather Condition |  |  | Rain | 2 | CC6 | CC6/CC6 | 605 | Overall | Overall | Overall | Overall | Preparation work | - | - | - | - | 15 | Indirect | Off site
Wind |  |  | <2rd | 3 | CC6 | CC6/Othere Country | 605/608 | Overall | Overall | Overall | Overall | Preparation work | - | - | - | - | 57 | Direct | On site |  |  |  | 30 driver 27 mid asians
|  |  |  | 4 | CC6 | CC6/CC6 | 605 | Overall | Overall | Mechanical | Critical and heavy | Preparation work | - | - | - | - | 15 | Direct | On site
General Personnel Summary / Общая сводка по мобилизации персонала |  |  |  | 5 | CC6 | CC6/CC6 | 605 | Overall | Overall | Civil | AG Concrete | Preparation work | - | - | - | - | 77 | Direct | On site
Total Manhours / Всего ч/ч |  |  | 10330 | 6 | CC6 | CC6/CC6 | 605 | Overall | Overall | Civil | AG Concrete | Preparation work | - | - | - | - | 22 | Direct | Off site
Total Direct / Всего рабочий персонал |  |  | 901 | 7 | CC6 | CC6/CC6 | 605 | Overall | Overall | Steel Structures | Primary Steel Structures | Preparation work | - | - | - | - | 84 | Direct | On site | Type of Machinery
Direct on Site / Рабочий персонал на площадке |  |  | 730 | 8 | CC6 | CC6/CC6 | 605 | Overall | Overall | Steel Structures | Primary Steel Structures | Preparation work | - | - | - | - | 6 | Direct | Off site | Crane | 23
Direct off site / Рабчий персонал вне площадки |  |  | 171 | 9 | CC6 | CC6/CC6 | 605 | Overall | Overall | Overall | Overall | Preparation work | - | - | - | - | 146 | Direct | On site | Loader | 3
Total Inderect / Всего непрямой персонал (ИТР) |  |  | 132 | 10 | CC6 | CC6/CC6 | 605 | Overall | Overall | Overall | Overall | Preparation work | - | - | - | - | 143 | Direct | Off site | Flatbed truck | 5 |  | Rest Immigration Bureau
On site |  |  |  | 11 | CC6 | CC6/CC6 | 605 | 605-015 | KM | Steel Structures | Primary Steel Structures | Preparation work | - | - | - | - | 6 | Direct | On site | Aerial Work Platforms | 3
Indirect Personnel / Непрямой персонал |  |  | 117 | 12 | CC6 | CC6/CC6 | 605 | 605-018 | KM | Steel Structures | Primary Steel Structures | Installation | tn | 665 | 44.9 | 44.9 | 5 | Direct | On site | Excavator | 5
Direct Personnel / Рабочий персонал |  |  | 730 | 13 | CC6 | CC6/CC6 | 605 | 605-010 | KMA | Steel Structures | Primary Steel Structures | Preparation work | - | - | - | - | 8 | Direct | On site | Forklift | 1
Off site |  |  |  | 14 | CC6 | CC6/CC6 | 605 | 605-024 | KMA | Steel Structures | Primary Steel Structures | Preparation work | - | - | - | - | 2 | Direct | On site | Road roller
Indirect Personnel / Непрямой персонал |  |  | 15 | 15 | CC6 | CC6/CC6 | 605/608 | 000-000 | Overall | General | Backfilling | Backfilling | m3 | 99256 | 50 | 43300 | 11 | Direct | On site
Direct Personnel / Рабочий персонал |  |  | 171 | 16 | CC6 | CC6/CC6 | 608 | 608-017 | KM | Steel Structures | Primary Steel Structures | Preparation work | - | - | - | - | 6 | Direct | On site
|  |  |  | 17 | CC6 | CC6/CC6 | 608 | 608-012 | KM | Steel Structures | Primary Steel Structures | Preparation work | - | - | - | - | 2 | Direct | On site
|  |  |  | 18 | CC6 | CC6/CC6 | 608 | 608-010 | KM | Steel Structures | Primary Steel Structures | Preparation work | - | - | - | - | 4 | Direct | On site
|  |  |  | 19 | CC6 | CC6/CC6 | 608 | 608-000 | Overall | UG Works | UG Piping Carbon Steel | Preparation work | - | - | - | - | 8 | Direct | On site
|  |  |  | 20 | CC6 | CC6/CC6 | 605 | 605-001 | Overall | Mechanical | Static Equipment | Preparation work | - | - | - | - | 9 | Direct | On site
|  |  |  | 21 | CC6 | CC6/CC6 | 605 | 605-008 | KM | Steel Structures | Primary Steel Structures | Installation | tn | 932.7 | 8.02 | 8.02 | 6 | Direct | On site
|  |  |  | 22 | CC6 | CC6/CC6 | 605 | 605-006 | KM | Steel Structures | Primary Steel Structures | Preparation work | - | - | - | - | 13 | Direct | On site
|  |  |  | 23 | CC6 | CC6/CC6 | 605 | 605-007 | KM | Steel Structures | Primary Steel Structures | Preparation work | - | - | - | - | 6 | Direct | On site
|  |  |  | 24 | CC6 | CC6/CC6 | 605 | 605-019 | Overall | UG Works | UG Piping Carbon Steel | Inspection | - | - | - | - | 2 | Direct | On site
|  |  |  | 25 | CC6 | CC6/CC6 | 605 | 605-019 | KM | Steel Structures | Primary Steel Structures | Installation | tn | 657 | 19.3 | 151.09 | 16 | Direct | On site
|  |  |  | 26 | CC6 | CC6/CC6 | 605 | 605-023 | KMA | Steel Structures | Primary Steel Structures | Preparation work | - | - | - | - | 4 | Direct | On site
|  |  |  | 27 | CC6 | CC6/CC6 | 605 | 605-020 | KM | Steel Structures | Primary Steel Structures | Inspection | - | - | - | - | 11 | Direct | On site
|  |  |  | 28 | CC6 | CC6/CC6 | 605 | 605-001 | KM | Steel Structures | Primary Steel Structures | Installation | tn | 1790 | 2.8 | 1026.94 | 4 | Direct | On site
|  |  |  | 29 | CC6 | CC6/CC6 | 608 | 608-009 | Overall | Civil | AG Concrete | Preparation work | - | - | - | - | 12 | Direct | On site
|  |  |  | 30 | CC6 | CC6/CC6 | 605 | 605-013 | Overall | Civil | AG Concrete | Preparation work | - | - | - | - | 32 | Direct | On site
|  |  |  | 31 | CC6 | CC6/CC6 | 608 | 608-015 | Overall | Civil | AG Concrete | Preparation work | - | - | - | - | 2 | Direct | On site
|  |  |  | 32 | CC6 | CC6/CC6 | 608 | 608-013 | Overall | Civil | UG Concrete | Preparation work | - | - | - | - | 19 | Direct | On site
|  |  |  | 33 | CC6 | CC6/CC6 | 608 | 608-018 | Overall | Civil | UG Concrete | Preparation work | - | - | - | - | 4 | Direct | On site
|  |  |  | 34 | CC6 | CC6/CC6 | 608 | 608-012 | ФOм1 | Civil | UG Concrete | Preparation work | - | - | - | - | 9 | Direct | On site
|  |  |  | 35 | CC6 | CC6/CC6 | 605 | 605-022 | Overall | Civil | UG Concrete | Preparation work | - | - | - | - | 22 | Direct | On site
|  |  |  | 36 | CC6 | CC6/CC6 | 608 | 608-001 | РCм1 | Civil | UG Concrete | Preparation work | - | - | - | - | 3 | Direct | On site
|  |  |  | 37 | CC6 | CC6/CC6 | 608 | 608-003 | РCм1 | Civil | UG Concrete | Preparation work | - | - | - | - | 2 | Direct | On site
|  |  |  | 38 | CC6 | CC6/CC6 | 605 | 605-015 | ФОм1 | Civil | AG Concrete | Preparation work | - | - | - | - | 17 | Direct | On site
|  |  |  | 39 | CC6 | CC6/CC6 | 605 | 605-016 | ПPм1 | Civil | UG Concrete | Reinforcement | tn | 42.18 | 3 | 39.5 | 17 | Direct | On site
|  |  |  | 40 | CC6 | CC6/CC6 | 605 | 605-005 | Overall | Civil | AG Concrete | Preparation work | - | - | - | - | 26 | Direct | On site
|  |  |  | 41 | CC6 | CC6/CC6 | 605 | 605-003 | Бм1 | Civil | AG Concrete | Reinforcement | tn | 6.7 | 3.4 | 6.7 | 15 | Direct | On site
|  |  |  | 42 | CC6 | CC6/CC6 | 605 | 605-003 | Бм1a | Civil | AG Concrete | Reinforcement | tn | 3.35 | 2 | 3.35
|  |  |  | 43 | CC6 | CC6/CC6 | 605 | 605-003 | Бм1г | Civil | AG Concrete | Reinforcement | tn | 3.33 | 2 | 3.33
|  |  |  | 44 | CC6 | CC6/CC6 | 605 | 605-009 | Overall | Civil | AG Concrete | Preparation work | - | - | - | - | 48 | Direct | On site
|  |  |  | 45 | CC6 | CC6/CC6 | 608 | 608-016 | РCм1 | Civil | UG Concrete | Concrete pouring | m3 | 205.85 | 49 | 161
|  |  |  | 46 | CC6 | CC6/CC6 | 608 | 608-016 | РCм2 | Civil | UG Concrete | Concrete pouring | m3 | 96.6 | 26 | 78
|  |  |  | 47 | CC6 | CC6/CC6 | 608 | 608-016 | РCм4 | Civil | UG Concrete | Concrete pouring | m3 | 38.64 | 15.32 | 30.64
|  |  |  | 48 | CC6 | CC6/CC6 | 608 | 608-016 | РCм5 | Civil | UG Concrete | Concrete pouring | m3 | 14.28 | 10.28 | 10.28
|  |  |  | 49 | CC6 | CC6/CC6 | 608 | 608-016 | РCм1-2 | Civil | UG Concrete | Concrete pouring | m3 | 10 | 7 | 7
|  |  |  | 50 | CC6 | CC6/CC6 | 608 | 608-016 | РCм1-3 | Civil | UG Concrete | Concrete pouring | m3 | 10 | 7 | 7
|  |  |  | 51 | CC6 | CC6/CC6 | 608 | 608-016 | РCм2-1 | Civil | UG Concrete | Concrete pouring | m3 | 17.2 | 13 | 13
|  |  |  | 52 | CC6 | CC6/CC6 | 608 | 608-016 | РCм2-2 | Civil | UG Concrete | Concrete pouring | m3 | 18.25 | 13 | 13
|  |  |  | 53 | CC6 | CC6/CC6 | 608 | 608-016 | РCм6 | Civil | UG Concrete | Concrete pouring | m3 | 13.48 | 9.48 | 9.48
|  |  |  | 54 | CC6 | CC6/CC6 | 608 | 608-016 | РCм7 | Civil | UG Concrete | Concrete pouring | m3 | 13.8 | 9.48 | 9.48
|  |  |  | 55 | CC6 | CC6/CC6 | 608 | 608-016 | РCм9 | Civil | UG Concrete | Concrete pouring | m3 | 10.48 | 7.48 | 7.48
|  |  |  | 56 | CC6 | CC6/CC6 | 608 | 608-016 | РCм10 | Civil | UG Concrete | Concrete pouring | m3 | 10.45 | 7.45 | 7.45
|  |  |  | 57 | CC6 | CC6/CC6 | 608 | 608-016 | РCм11 | Civil | UG Concrete | Concrete pouring | m3 | 8.48 | 6.96 | 6.96
|  |  |  | 58 | CC6 | CC6/CC6 | 608 | 608-008 | Фм1 | Civil | UG Concrete | Concrete pouring | m3 | 37.39 | 25 | 37.39
|  |  |  | 59 | CC6 | CC6/CC6 | 608 | 608-008 | Фм2 | Civil | UG Concrete | Concrete pouring | m3 | 87.18 | 75 | 87.18
|  |  |  | 60 | CC6 | CC6/CC6 | 608 | 608-008 | Фм3 | Civil | UG Concrete | Concrete pouring | m3 | 33.67 | 24 | 33.67
|  |  |  | 61 | CC6 | CC6/CC6 | 608 | 608-008 | РCм1 | Civil | UG Concrete | Concrete pouring | m3 | 8.51 | 3 | 8.51
|  |  |  | 62 | CC6 | CC6/CC6 | 608 | 608-008 | РCм2 | Civil | UG Concrete | Concrete pouring | m3 | 4.91 | 1.4 | 4.91
|  |  |  | 63 | CC6 | CC6/CC6 | 608 | 608-008 | РCм3 | Civil | UG Concrete | Concrete pouring | m3 | 28.86 | 3.98 | 28.86
|  |  |  | 64 | CC6 | CC6/CC6 | 608 | 608-008 | РCм4 | Civil | UG Concrete | Concrete pouring | m3 | 15.59 | 3 | 15.59
|  |  |  | 65 | CC6 | CC6/CC6 | 608 | 608-008 | РCм5 | Civil | UG Concrete | Concrete pouring | m3 | 18.14 | 3 | 18.14
|  |  |  | 66 | CC6 | CC6/CC6 | 608 | 608-008 | РCм6 | Civil | UG Concrete | Concrete pouring | m3 | 22.42 | 5 | 22.42
|  |  |  | 67 | CC6 | CC6/CC6 | 608 | 608-008 | РCм7 | Civil | UG Concrete | Concrete pouring | m3 | 19.16 | 4 | 19.16
|  |  |  | 68 | CC6 | CC6/CC6 | 608 | 608-008 | РCм8 | Civil | UG Concrete | Concrete pouring | m3 | 60.08 | 13 | 60.08
|  |  |  | 69 | CC6 | CC6/CC6 | 608 | 608-008 | РCм4-1 | Civil | UG Concrete | Concrete pouring | m3 | 16.13 | 3.54 | 16.13
|  |  |  | 70 | CC6 | CC6/CC6 | 605 | 605-001 | Overall | Piping | AG Piping - PREFAB | Welding | DI | 24534 | 24 | 3977.2
|  |  |  | 71 | CC6 | CC6/CC6 | 605 | 605-003 | Overall | Piping | AG Piping - PREFAB | Welding | DI | 44788 | 76 | 11651.2
|  |  |  | 72 | CC6 | CC6/CC6 | 605 | 605-005 | Overall | Piping | AG Piping - PREFAB | Welding | DI | 21838 | 30 | 5669.8
|  |  |  | 73 | CC6 | CC6/CC6 | 605 | 605-007 | Overall | Piping | AG Piping - PREFAB | Welding | DI | 1791 | 28 | 410.8
|  |  |  | 74 | CC6 | CC6/CC6 | 605 | 605-008 | Overall | Piping | AG Piping - PREFAB | Welding | DI | 22330 | 56 | 4879.2
|  |  |  | 75 | CC6 | CC6/CC6 | 605 | 605-009 | Overall | Piping | AG Piping - PREFAB | Welding | DI | 31718 | 100 | 8434.6
|  |  |  | 76 | CC6 | CC6/CC6 | 605 | 605-010 | Overall | Piping | AG Piping - PREFAB | Welding | DI | 21078 | 20 | 6170.6
|  |  |  | 77 | CC6 | CC6/CC6 | 605 | 605-011 | Overall | Piping | AG Piping - PREFAB | Welding | DI | 6815 | 4 | 2056.6
|  |  |  | 78 | CC6 | CC6/CC6 | 605 | 605-012 | Overall | Piping | AG Piping - PREFAB | Welding | DI | 19016 | 4 | 3643.2
|  |  |  | 79 | CC6 | CC6/CC6 | 605 | 605-014 | Overall | Piping | AG Piping - PREFAB | Welding | DI | 5232 | 15.2 | 1176.8
|  |  |  | 80 | CC6 | CC6/CC6 | 605 | 605-015 | Overall | Piping | AG Piping - PREFAB | Welding | DI | 6739 | 46 | 1918.4
|  |  |  | 81 | CC6 | CC6/CC6 | 605 | 605-018 | Overall | Piping | AG Piping - PREFAB | Welding | DI | 10050 | 26 | 3300.4
|  |  |  | 82 | CC6 | CC6/CC6 | 605 | 605-019 | Overall | Piping | AG Piping - PREFAB | Welding | DI | 5007 | 4 | 744
|  |  |  | 83 | CC6 | CC6/CC6 | 605 | 605-022 | Overall | Piping | AG Piping - PREFAB | Welding | DI | 32941 | 115.6 | 7930
|  |  |  | 84 | CC6 | CC6/CC6 | 608 | 608-008 | Overall | Piping | AG Piping - PREFAB | Welding | DI | 10345 | 28 | 2296
|  |  |  | 85 | CC6 | CC6/CC6 | 608 | 608-009 | Overall | Piping | AG Piping - PREFAB | Welding | DI | 12922 | 20 | 1460
|  |  |  | 86 | CC6 | CC6/CC6 | 608 | 608-014 | Overall | Piping | AG Piping - PREFAB | Welding | DI | 2079 | 22 | 123.2
|  |  |  | 87 | CC6 | CC6/CC6 | 608 | 608-015 | Overall | Piping | AG Piping - PREFAB | Welding | DI | 18645 | 44 | 886
[20 empty] | Total Machinery |  | 40
·
Report Number :
[END OF DOCUMENT / КОНЕЦ ДОКУМЕНТА]
Note on Z39: 吊车 160T履带吊 30T吊车 2 25T吊车 2 400T 55T 30T 3 80T
Note on Y40: 装载机
Note on Y41: 平板车
Note on Y42: 曲臂车
Note on Y43: 挖掘机
Note on Y44: 叉车

## Lists
Discipline / Дисциплина | Work type / Вид работ | Activity Name / Название работы | UOM / Ед. изм. | Direct - Indirect / Рабочий - ИТР | On site - off site / на площадке - вне площадки
Civil | Piling | Preparation work | PCS | Direct | On site
UG Works | UG Concrete | Driven | m2 | Indirect | Off site
Steel Structures | AG Concrete | Headcut | m3
Piping | Pre-cast Concrete | Lean concrete | %
Electrical & Instrumentation | Primary Steel Structures | Reinforcement | tn
General | Secondary Steel Structures | Formwork | m
Mechanical | UG Piping Carbon Steel | Concrete pouring | DI
Painting & Insulation | UG Piping HDPE | Installation | -
Building | Manholes | Bolt tightening
Overall | AG Piping - PREFAB | Grout release
| AG Piping - SITE | Inspection
| Backfilling | Excavation
| Excavation | Pipeline or manholes inst.
| Grounding / Earthing and Lightning | Backfilling
| Critical and heavy | Welding
Static Equipment
Rotating Equipment
Instrumentation Cable pulling
Ductwork
HVAC mian equipment
False floor
Fire Fighting Works - Main Equipment
Passive Fire Protection (touch-up)
Roads & Paving - Concrete
Installations in the field
Insulation
Cladding
Overall